## Sheet1
Task to implement | Date of completion | Planned Date | Assigend person | Notes
Design | 2017-02-26 | 2017-02-26 | William & Cedrik | Went well
UI | 2017-04-06 | 2017-03-11 | Cedrik | Implementation of new elements
Map Generation | 2017-03-21 | 2017-03-11 | William | Simple to implement
HUD | 2017-05-06 | 2017-03-18 | Cedrik | Testing on others
Tanks Moving | 2017-03-23 | 2017-03-18 | William | On time ~
Weapons | 2017-04-06 | 2017-03-25 | William & Cedrik | Textures took longer to adjust
Save/Load | 2017-05-03 | 2017-04-04 | William | Had to wait for other implementations
Leaderboard | 2017-05-11 | 2017-04-11 | William & Cedrik | Game mechanics had to be implemented
Sound | 2017-05-10 | 2017-04-15 | Cedrik | Pushed at the end due to optimization issued
Physics | 2017-03-28 | 2017-04-24 | William | Implemented earlier
Game Mechanics | 2017-05-06 | 2017-04-27 | William & Cedrik | Added non-planned features (i.e. rotation)
AI | 2017-05-06 | 2017-04-30 | William | Works with multiple AI
Testing/Debugging | 2017-05-19 | 2017-05-04 | William & Cedrik | Game does not crash